## Slide 1
Team meeting, 2 October
Decisions and next steps

## Slide 2
What we decided
Move the launch to 4 November
Hire one more support person before launch
Send the sales report every Monday

## Slide 3
Where we are
12 of 15
Launch tasks done
2
Roles still open
4 Nov
New launch date

## Slide 4
Who does what
Task | Team | Due
Final prices | Finance | 10 Oct
Launch page | Marketing | 20 Oct
Support training | Support | 28 Oct

## Slide 5
The next four weeks
01
This week
Post the support job
02
Mid October
Prices and launch page ready
03
4 November
Launch